## Sheet1
Start Date | End Date | Description | Duration
Mar 31 2020 | Apr 8 2020 | Gantt Chart | 9 Days
Apr 5 2020 | Apr 7 2020 | Project Update 1 | 2 Days
Apr 12 2021 | Apr 14 2020 | Project Update 2 | 2 Days
Apr 19 2022 | Apr 21 2020 | Project Update 3 | 2 Days
Apr 26 2023 | Apr 28 2020 | Project Update 4 | 2 Days
May 3 2020 | May 5 2020 | Project Update 5 | 2 Days
Apr 10 2023 | May 12 2020 | Project Update 6 | 2 Days
May 17 2020 | May 19 2020 | Project Update 7 | 2 Days
May 24 2020 | May 26 2020 | Project Update 8 | 2 Days
Mar 31 2020 | Apr 15 2020 | Planning Report | 16 Days
Mar 31 2021 | Apr 21 2020 | Literature Review | 22 Days
Apr 15 2020 | May 6 2020 | PFD | 14 Days
Apr 22 2020 | Apr 29 2020 | L1 Simulation | 7 Days
Apr 29 2020 | May 6 2020 | L2 Simulation | 7 Days
May 6 2020 | May 27 2020 | Final Project | 21 Days
May 6 2020 | May 13 2020 | Economic Analysis | 7 Days
May 6 2020 | May 13 2020 | Environment, Health, and Safety (EH&S) | 7 Days
Planning Report |  | Literature Review |  | L1 Simulation | L2 Simulation
Abstract | Shi | Format |  | Simulation | Simulation
BFD | Shi | Design - Separation |  | Stream Table | PFD
Initial Kinetic Data | Leon | Design - Reactions |  | Equipment List | Stream Table
Thermodymamic Package | Leon | Design - Safety |  | Mass Balance Check | Equipment List
Cost Estimate | Tora | Design - Risk |  |  | Mass Balance Check
Design - Economics
Major Findings
Useful Stuff for Our Project
Final Report |  | Economic analysis |  | EH&S
Letter of Transmittal |  | Capital Costs |  | Environmental Factors
Cover Page |  | Manufacturing Costs |  | Health Factors
Table of Contents |  | Profitability |  | Safety Factors
Abstract |  | Cash Flow Diagrams
Introduction
Process Flow Diagram + Mass Bal
Process Description
Energy Balance and Utility Requirements
Equipment List and Unit Descriptions
Equipment Specification Sheets
Equipment Cost Summary
Fixed Capital Investment Summary
Safety, Health, and Environmental Considerations
Process Safety Considerations
List of waste streams and BACT to treat waste prior to discharge.
Other Important Considerations
Manufacturing/Operation Costs (exclusive of Capital Requirements)
Economic Analysis
Conclusions and Recommendations
Acknowledgements
Bibliography
Appendix